## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status (Open/Closed) | Remarks
1 | Imran | 2026-01-05 | File upload fails for large PDF files | Sprint 1 | Imran | Functional | Added file size validation and optimized upload logic | 2026-01-08 | Closed | Working as expected
2 | Imran | 2026-01-06 | Extracted text contains special character issues | Sprint 1 | Imran | Data | Implemented text cleanup and encoding fix | 2026-01-08 | Closed | Verified with multiple documents
3 | Imran | 2026-01-07 | DOCX files not processed correctly | Sprint 1 | Imran | Functional | Fixed DOCX parsing logic | 2026-01-08 | Closed | No errors observed
4 | Imran | 2026-01-10 | Search results not ranked properly | Sprint 2 | Imran | Performance | Improved relevance scoring logic | 2026-01-18 | Open | Needs further tuning
5 | Imran | 2026-01-12 | Chatbot response delayed for large document sets | Sprint 2 | Imran | Performance | Added basic caching mechanism | 2026-01-18 | Open | Monitoring performance
6 | Imran | 2026-01-14 | UI misalignment on document upload screen | Sprint 2 | Imran | UI | Corrected CSS styling | 2026-01-18 | Closed | UI verified
7 | Imran | 2026-01-16 | Incorrect error message shown for unsupported file types | Sprint 2 | Imran | Usability | Updated validation messages | 2026-01-18 | Closed | Improved user feedback
8 | Imran | 2026-03-19 | Duplicate documents allowed during upload | Sprint 3 | Imran | Functional | Added duplicate check using hash comparison | 2026-03-28 | Closed | Duplicate prevention working

## Sheet2
Logical
User Interface
Maintainability
Standards
Others